## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: BuzzFeed | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof. Ujwala Pagare | [6 empty] | DATE: | [11 empty] | 2025-04-02
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Aayush Balip, Sujal Jain, Keval Shah | 2025-01-06 | 2025-01-09 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | Identifying the functionalities of the Mini Project | Aayush Balip, Sujal Jain, Keval Shah | 2025-01-08 | 2025-01-14 | 2 | 100% | bar: WEEK 1 W to WEEK 2 T; WEEK 3 T
1.3 | Discussing the project topic with the help of paper prototype. | Aayush Balip, Sujal Jain, Keval Shah | 2025-01-15 | 2025-02-10 | 2 | 100% | bar: WEEK 2 W to WEEK 6 M
1.4 | Designing the Graphical User Interface(GUI) | Sujal Jain, Keval Shah | 2025-02-05 | 2025-02-10 | 3 | 100% | bar: WEEK 5 T to WEEK 6 M
1.5 | Presentation I | Aayush Balip, Sujal Jain, Keval Shah | 2024-02-11 | 2025-02-11 | 1 | 100% | bar: WEEK 6 T
2 | Project Design and Implementation
2.1 | Database Design | Keval Shah, Sujal Jain | 2025-02-06 | 2025-02-13 | 1 | 100% | bar: WEEK 5 T to WEEK 6 T
2.2 | Database Connectivity of all modules | Aayush Balip, Keval Shah | 2025-02-10 | 2025-02-21 | 1 | 100% | bar: WEEK 6 M to WEEK 7 F
2.3 | Integration of all modules and Report Writing | Sujal Jain, Keval Shah | 2025-02-24 | 2025-04-01 | 1 | 100% | bar: WEEK 8 M to WEEK 13 T
2.4 | Presentation II | Sujal Jain, Keval Shah | 2025-04-02 | 2025-04-02 | 1 | 100% | bar: WEEK 13 W